Project Plan: Sales Supply Chain Efficiency Improvement

1. Executive Summary

Sales analysis reveals that the Average Shipping Time is approximately 4 days, posing a significant challenge to operational efficiency and customer satisfaction. The goal of this project is to identify the root causes of this delay and reduce the Average Shipping Time by 25% within two months, by analyzing order/shipment data and deploying pilot solutions to the slowest-performing regions or carriers.

2. Project Goal

To reduce the average shipping time per order from 3.96 days to less than 3 days, thereby enhancing the Customer Experience and increasing the Customer Retention Rate.

3. Scope of Work

| In Scope | Out of Scope |
| --- | --- |
| Data Analysis: Utilizing Order Date and Ship Date columns 3to calculate the time difference for every order4. | Radical changes to carrier contracts or primary vendor changes. |
| Root Cause Identification: Identifying the "slowest shipping methods" (e.g., Standard Class) 5and the "slowest cities in delivery"6. | Analyzing inventory issues (Demand Forecasting) 7or marketing budget allocation (Market Optimization)8. |
| Pilot Implementation: Testing rapid solutions in a single geographical region (the slowest one identified). | Purchasing new equipment or making major capital investments in warehouses. |

4. Work Plan and Timeline

Phase I: Analysis and Root Cause Identification (October 2025)

| Approximate Date | Key Activity (Deliverable) | Detailed Steps and Actions |
| --- | --- | --- |
| Week 1 (Oct 1 - 7) | Data Collection & Preparation | 1. Extract all order data containing Order Date and Ship Date9. 2. Calculate a new column: Shipping Duration (in days) for every order. |
| Week 2 (Oct 8 - 14) | Root Cause Analysis | 1. Generate a report identifying the slowest carrier performance10. 2. Generate a report identifying the slowest 3 cities or geographical regions11. 3. Define the most suitable region/city for the pilot test. |
| Week 3 (Oct 15 - 21) | Solution Design & Pilot Planning | 1. Formulate 2-3 rapid solutions (e.g., adjusting daily pickup times, or using an alternative carrier for the slow region). 2. Determine the Baseline Metrics (current average shipping time) for the target pilot region. |
| Week 4 (Oct 22 - 31) | Pilot Plan Approval | 1. Review the pilot plan with stakeholders (Operations/Logistics Manager). 2. Obtain final approval to begin implementing solutions in the designated pilot area. |

Phase II: Pilot Implementation and Evaluation (November 2025)

| Approximate Date | Key Activity (Deliverable) | Detailed Steps and Actions |
| --- | --- | --- |
| Week 1 (Nov 1 - 7) | Pilot Implementation | 1. Apply the approved solution (e.g., carrier change or packing process adjustment) to all orders destined for the pilot region. 2. Train the operations team on the new procedures. |
| Week 2 (Nov 8 - 14) | Monitoring & Data Logging | 1. Daily monitoring of shipping duration for new orders in the pilot region. 2. Accurately log data on any new delays to determine if they are related to the new process. |
| Week 3 (Nov 15 - 21) | Results Analysis & Initial Reporting | 1. Compare the post-implementation average shipping time against the October baseline. 2. Prepare an initial report for the Operations Manager on the success of the pilot solution. |
| Week 4 (Nov 22 - 30) | Decision & Scaling | 1. Hold a final review meeting to discuss the results. 2. Scale Decision: If the solution was successful, draft a plan to roll it out to all other slow-performing regions in the following month. If unsuccessful, return to Phase I for alternative solution design. |

5. Key Success Metrics

| Metric | Baseline Value | Target |
| --- | --- | --- |
| Average Shipping Time | 3.96 days 12 | Less than 3.0 days |
| Delayed Shipments % | (To be calculated in Week 2 of October) | Reduce the baseline percentage by 50% |
| Customer Satisfaction (CSAT - Logistics) | (Requires customer survey data) | Increase the rate of customers describing shipping as "Fast" or "On-Time" |